## Plan Overview
Self-Healing Automation
Sprint | Date Range | Phase | Focus | Demo Date | Success Criteria
Sprint 1 | Mon Apr 27 to Fri May 1 | Planning & Foundations | Agreed what to build and how. |  | Architecture and tech stack signed off.
Sprint 2 | Mon May 4 to Fri May 8 | Scanner & Crawler | Reading pages and whole sites into Excel. |  | A user can scan any site and see every field listed in Excel.
Sprint 3 | Mon May 11 to Fri May 15 | Runner & Self-Healing | Running tests and recovering when pages change. |  | Tests still finish when the form changes.
Sprint 4 | Mon May 18 to Fri May 22 | Scenario Recording | Record once, replay later. | Fri May 22 | A non technical user can record once and replay reliably later.
Sprint 5 | Mon May 25 to Fri May 29 | AI Test Cases, Part 1 | Generate happy-path variants from a recording. | Fri May 29 | One recording produces at least five working tests without manual edits.
Sprint 6 | Mon Jun 1 to Fri Jun 5 | AI Test Cases, Part 2 | Negative cases, review screen, reports. | Fri Jun 5 | A user goes from one recording to approved and executed AI tests in one sitting.

## Detailed Tasks
Detailed Task Plan
Sprint | Phase | Date Range | Sub-Task | Description | Demo Date | Owner | Status
Sprint 1 | Planning & Foundations | Mon Apr 27 to Fri May 1 | Problem framing | Agreed what self-healing means for our tool. |  | Aditya | Done
Sprint 1 | Planning & Foundations | Mon Apr 27 to Fri May 1 | Tech choices | Picked Playwright, Streamlit, and a local AI model so nothing leaks externally. |  | Aditya | Done
Sprint 1 | Planning & Foundations | Mon Apr 27 to Fri May 1 | Storage approach | Settled on plain text files on disk for every artifact. |  | Aditya | Done
Sprint 1 | Planning & Foundations | Mon Apr 27 to Fri May 1 | Anti-bot handling | Figured out how to avoid being blocked by target sites. |  | Aditya | Done
Sprint 1 success criteria | Architecture and tech stack signed off.
Sprint 2 | Scanner & Crawler | Mon May 4 to Fri May 8 | Page scanner | Lists every input, button, and dropdown on a page. |  | Aditya | Done
Sprint 2 | Scanner & Crawler | Mon May 4 to Fri May 8 | Site crawler | Walks a whole site and scans each page it finds. |  | Aditya | Done
Sprint 2 | Scanner & Crawler | Mon May 4 to Fri May 8 | Excel export | Saves each scan as an Excel sheet for review. |  | Aditya | Done
Sprint 2 | Scanner & Crawler | Mon May 4 to Fri May 8 | Library screen | Lists past scans and lets users open them. |  | Aditya | Done
Sprint 2 success criteria | A user can scan any site and see every field listed in Excel.
Sprint 3 | Runner & Self-Healing | Mon May 11 to Fri May 15 | Action runner | Runs the steps of a scenario, clicking and typing as needed. |  | Aditya | Done
Sprint 3 | Runner & Self-Healing | Mon May 11 to Fri May 15 | Self-healing | Tries alternative locators, then the AI, if the original fails. |  | Aditya | Done
Sprint 3 | Runner & Self-Healing | Mon May 11 to Fri May 15 | Multi-page flows | A scenario can move across several pages. |  | Aditya | Done
Sprint 3 | Runner & Self-Healing | Mon May 11 to Fri May 15 | Reports view | Shows pass and fail history and flags self-healed steps. |  | Aditya | Done
Sprint 3 | Runner & Self-Healing | Mon May 11 to Fri May 15 | Smart test data | Fills fields with realistic values instead of dummy text. |  | Aditya | Done
Sprint 3 success criteria | Tests still finish when the form changes.
Sprint 4 | Scenario Recording | Mon May 18 to Fri May 22 | In-page capture | Records the user's clicks, typing, and dropdown changes. | Fri May 22 | Aditya | In Progress
Sprint 4 | Scenario Recording | Mon May 18 to Fri May 22 | Multiple locators | Stores several ways to find each field for safer replay. | Fri May 22 | Aditya | In Progress
Sprint 4 | Scenario Recording | Mon May 18 to Fri May 22 | Encrypted login | Saves the login session so users do not re-login on replay. | Fri May 22 | Aditya | In Progress
Sprint 4 | Scenario Recording | Mon May 18 to Fri May 22 | Recordings screen | Lists past recordings and plays them back. | Fri May 22 | Aditya | In Progress
Sprint 4 | Scenario Recording | Mon May 18 to Fri May 22 | Round-trip test | A saved recording still replays after closing and reopening the tool. | Fri May 22 | Aditya | In Progress
Sprint 4 | Scenario Recording | Mon May 18 to Fri May 22 | MILESTONE DEMO | Record a fresh scenario live, save, reload, and replay on a slightly changed page. | Fri May 22 | Aditya | Planned
Sprint 4 success criteria | A non technical user can record once and replay reliably later.
Sprint 5 | AI Test Cases, Part 1 | Mon May 25 to Fri May 29 | Happy variants | From one recording, generate several runs with different realistic data. | Fri May 29 | Aditya | Planned
Sprint 5 | AI Test Cases, Part 1 | Mon May 25 to Fri May 29 | Persist cases | Save generated cases next to the recording so they survive restarts. | Fri May 29 | Aditya | Planned
Sprint 5 | AI Test Cases, Part 1 | Mon May 25 to Fri May 29 | Reuse runner | Run each generated case through the existing replay engine. | Fri May 29 | Aditya | Planned
Sprint 5 | AI Test Cases, Part 1 | Mon May 25 to Fri May 29 | MILESTONE DEMO | Generate five or more variants from one recording and run them. | Fri May 29 | Aditya | Planned
Sprint 5 success criteria | One recording produces at least five working tests without manual edits.
Sprint 6 | AI Test Cases, Part 2 | Mon Jun 1 to Fri Jun 5 | Negative cases | Generate broken inputs on purpose to test how the app handles bad data. | Fri Jun 5 | Aditya | Planned
Sprint 6 | AI Test Cases, Part 2 | Mon Jun 1 to Fri Jun 5 | Review screen | Tab to read, edit, approve, or discard each generated test. | Fri Jun 5 | Aditya | Planned
Sprint 6 | AI Test Cases, Part 2 | Mon Jun 1 to Fri Jun 5 | Failure reasons | When a test fails, say in plain English if the data was wrong or the page changed. | Fri Jun 5 | Aditya | Planned
Sprint 6 | AI Test Cases, Part 2 | Mon Jun 1 to Fri Jun 5 | Per-case reports | Reports screen shows pass and fail per generated test plus any self-healing. | Fri Jun 5 | Aditya | Planned
Sprint 6 | AI Test Cases, Part 2 | Mon Jun 1 to Fri Jun 5 | MILESTONE DEMO | Record once, generate cases, review and approve, run them, and show the report. | Fri Jun 5 | Aditya | Planned
Sprint 6 success criteria | A user goes from one recording to approved and executed AI tests in one sitting.

## Demo Schedule
Upcoming Demos
Sprint | Demo Date | What we showcase
Sprint 4 | Fri May 22 | Record a fresh scenario live, save, reload, and replay on a slightly changed page.
Sprint 5 | Fri May 29 | Generate five or more variants from one recording and run them.
Sprint 6 | Fri Jun 5 | Record once, generate cases, review and approve, run them, and show the report.

## Risks & Assumptions
Risks and Assumptions
Type | Item | Mitigation